## Sheet1
ISO/IEC JTC 1/SC 22/OWG V N 0167, Schedule for PDTR Ballot, prepared 22 October 2008
Start Date | Event | Days required | Completed Date
2008-04-14 | Leave meeting with disposition of comments | 0 | 2008-04-14
2008-04-14 | Action items completed | 14 | 2008-04-28
2008-04-28 | Editor revises draft | 14 | 2008-05-12
2008-05-12 | Reviewers check draft | 7 | 2008-05-19
2008-05-19 | Editor revises draft | 7 | 2008-05-26
2008-05-26 | Working group review | 28 | 2008-06-23
2008-06-23 | Secretary consolidates comments | 0 | 2008-06-23
2008-06-23 | Contingency | 7 | 2008-06-30
2008-06-30 | Editors meeting | 7 | 2008-07-07
2008-07-07 | Editor revises draft | 14 | 2008-07-21
2008-07-21 | Reviewers check draft | 7 | 2008-07-28
2008-07-28 | Editor revises draft | 7 | 2008-08-04
2008-08-04 | Send to working group for review | 28 | 2008-09-01
2008-09-01 | Secretary consolidates comments | 0 | 2008-09-01
2008-09-01 | Contingency | 14 | 2008-09-15
2008-09-15 | Review of Pre-meeting mailing | 14 | 2008-09-29
2008-09-29 | Stuttgart meeting | 7 | 2008-10-06
2008-10-06 | Action items completed | 14 | 2008-10-20
2008-10-20 | Editor revises draft | 14 | 2008-11-03
2008-11-03 | Reviewers check draft | 7 | 2008-11-10
2008-11-10 | Editor revises draft | 7 | 2008-11-17
2008-11-17 | PDTR ballot - During the ballot, there will be an Editors' web/telecon (9 December) - to consider material to be added | 126 | 2009-03-23
2009-03-23 | Contingency | 21 | 2009-04-13
2009-04-13 | Meeting # 10 - San Diego, 15-17 April 2009 | 7 | 2009-04-20
2009-04-20 | Action items completed | 14 | 2009-05-04
2009-05-04 | Editor revises draft | 14 | 2009-05-18
2009-05-18 | Reviewers check draft | 7 | 2009-05-25
2009-05-25 | Editor revises draft | 7 | 2009-06-01
2009-06-01 | DTR ballot - During the ballot, there will be Meeting # 11, Canada, 13-15 July 2009 - to consider future work | 126 | 2009-10-05
This would seem to suggest that Meeting #11 should occur no earlier than 5 October 2009
Formulas:
Completed Date = [Start Date]+[Days required]
Completed Date = [Completed Date, row above]+[Days required]
Start Date = [Completed Date, row above]