## Action Item Log
ISO/IEC JTC 1/SC 22/WG 23/S 0001 |  |  |  | Updated: | 2013-09-20
Action Item Log for ISO/IEC JTC 1/SC 22/OWGV
Label | Mtg-Item Number | Assignee | Item | Status | Comments | Date of Last Status
Action | #27-2 | Michell, Stephen | Work with the editor of 17960 and get the disposition of comments to the SC 22 secretary for CD 2 ballot of 17960. | Open
Action | #27-1 | Wagoner, Larry | Submit the draft of CD 17960 approved at the meeting to the SC 22 secretary | Open
Action | #26-3 | Pygott, Benito | Research Code Signing existing practice | Open |  | 2013-06-09
Action | #26-2 | Pgott | Reword 4.12 of 17960 to remove the word verbatim. | Closed | The editor has control of the document | 2013-06-09
Action | #26-1 | Pygott | Review MISRA-C references in TR 24772, | Closed | Review, to be incorporated into 24772. | 2013-06-07
Action | #24-1 | Ploedereder | Identify a new point of contact for the SPARK programming language. | Closed |  | 2013-06-07
Action | #23-1 | Benito | The Convener will work with WG 21 to co-locate for June 2014 | Closed |  | 2013-06-07
Action | #23-2 | Michell | Review changes in the Ada revision to see how Annex C may be affected | Open |  | 2012-09-13
Action | #23-3 | Benito, Jaeschke | Contact Ecma TC 39 and try to get new contacts to renew the liaison to ECMAScript | Closed |  | 2012-12-12
Action | #23-4 | Keaton | Distribute information on the PHP include issue for education and consideration | Closed |  | 2012-12-12
Action | #23-5 | Benito | Contact CWE to discuss inclusion of TR 24772 in CWE, CVE, etc in the related efforts pages | Closed |  | 2012-09-15
Action | #22-01 | Benito | The convener will check availability at ANSI for Meeting #25. He will schedule it in New York or Washington accordingly, at a date adjacent to 20-22 March 2013. | Closed |  | 2012-07-02
Action | #22-02 | Benito | Close on plans to colocate meeting #26 with WG9. The dates would be 8-10 June 2013. | Closed |  | 2012-12-12
Action | #22-03 | Ploedereder | Provide a logistics document for meeting #26. | Closed | See N0437 | 2013-02-18
Action | #22-04 | Benito, Moore | Remove MUMPS and UML from future agendas. | Closed |  | 2012-09-12
Action | #22-05 | Coyne | Revise the PHP annex based on N0407 and provide to convener and secretary by 30 June. | Closed | See N0411 | 2012-07-02
Action | #22-06 | Benito | Add PHP annex (to be received from Coyne) to the next balloting draft. | Closed | See N0409 | 2012-07-02
Action | #22-07 | Benito | Incorporate the comment disposition of N0403 into the next balloting draft | Closed | See N0409 | 2012-07-02
Action | #22-08 | Benito | Contact Japan national body to invite more specifics related to PDTR comment JP-7 on the next round of balloting. | Closed |  | 2012-06-25
Action | #22-9 | Keaton | Lead a group in drafting a more complete proposal, based on [N0408] to merge XZI into FLC--both for the body of the document and the annexes. | Closed | See CA-10 N0421 | 2012-09-13
Action | #22-10 | All | Any National Body is invited to offer a comment to merge XZI into FLC during the PDTR2 ballot. | Closed | See N0417 | 2012-09-12
Action | #22-11 | Benito | Investigate providing a set of links to the language specifications of each of the languages we are considering. This would include obtaining copies of the specifications, putting them on the website with appropriate protection, and making links available. | Closed |  | 2012-09-12
Action | #22-12 | Benito | Prepare skeleton of Standing Document [S0005] describing the relationship of 24772 to CWE. | Open |  | 2012-06-22
Action | #22-13 | All | Consider volunteering to perform periodic analysis of relationship between evolving CWE and evolving 24772 to provide content for [S0005]. See the minutes [N0403] for additional details. | Open |  | 2012-06-22
Action | #22-14 | Benito | Incorporate N0406 into the next balloting draft. | Closed | See N0410 | 2012-09-12
Action | #21-6 | Michell | Prepare for and lead discussion of "Promotion of WG23 Products" at every meeting. | Standing |  | 2012-04-03
Action | #21-1 | Benito | Take whatever steps are necessary to terminate the inactive liaison with MISRA-L | Clsoed | The secretary removed this item from the agenda for Meeting #22 (which predated the recording of the AI). This action can be completed by the plenary meeting at Geneva. John will put it in his convener's report. | 2012-09-12
Action | #20-3 | Benito | Prepare a logistics document for Meeting #23 in Geneva | Closed | John is waiting for information from the host. Preliminary information for this meeting was posted to the WG 23 web site on 04-04-12 as N0395. John will check with the Secretariat to see if there is more info. | 2012-09-12
Action | #21-5 | Benito | Add "Promotion of WG23 Products" as an agenda item on all future meetings. | Closed | The Secretary added this item to the agenda for Meeting #22 (which predated the recording of the AI.) | 2012-09-12
Action | #21-9 | Johnson | Recruit some SQL expertise to finish drafting an SQL annex. | Closed | Some done, but no progress last year. Closed administratively | 2012-04-03
Action | #12-04 | Moore | Check MITRE for availability to host Meeting #14 during weeks of June 21 and June 28. | Closed | OBE | 2010-03-28
Action | #12-03 | Nagle | Check GMU for availability to host Meeting #14 during weeks of June 21 and June 28. | Closed | OBE | 2010-03-28
Action | #12-01 | Benito | Check INCITS for availability to host Meeting #14 during weeks of June 21 and June 28. | Closed | OBE | 2010-03-28
Action | #21-7 | All | Each member of the working group should review the drafted PHP annex [N0393] and provide comments to Kevin Coyne. | Closed |  | 2012-06-20
Action | #20-1 | Benito | Follow-up on idea of who might be recruited to draft a C++ annex | Closed |  | 2012-06-20
Action | #21-2 | Wagoner | Draft an introduction for WD 17960. | Closed | Included in N0399 | 2012-06-18
Action | #21-3 | Wagoner | Suggest some terms and definitions to be added to WD 17960, including "digital signature" from ISO/IEC 13888-1, IT Security Techniques | Closed | Included in N0399 | 2012-06-18
Action | #21-4 | Wagoner | Revise WD 17960 considering AI #21-2, #21-3, and the meeting #21 markup [N0394] | Closed | See N0399 | 2012-06-18
Action | #21-8 | All | If any national body wants the PHP annex included in the second edition of the TR, they should note this in their NB comments. | Closed | See CA-2 of N0397 | 2012-06-18
Action | #20-5 | Michell | Rewrite 6.39 in terms of threads rather than tasks as well as propose any collateral changes. This could be submitted as part of Canada's comments. (It would be OK to circulate it informally before or during the ballot.) | Closed | See N0397 | 2012-06-18
Action | #11-03 | Nagle, Benito | Revise [N0216] in accordance with the new format and circulate it to J3 and WG5. | Closed | WG 5 document N1915 will be discussed at the next WG 5 meeting in June. | 2012-04-18
Action | #18-07 | Johnson | Consult with his SQL contact to attempt to answer some of the open questions and revise the draft annex accordingly. | Closed | Closed administratively and replaced by #21-9. | 2012-03-28
Action | #20-2 | Michell | Follow-up on idea of who might be recruited to draft a C++ annex | Closed | Steve chatted with persons at IBM with little result. | 2012-03-28
Action | #20-4 | Benito | Consider whether it if feasible to colocate with WG9 in Berlin in June 2013 and commit if appropriate | Closed | We have committed. We will have dates soon. | 2012-03-28
Action | #20-6 | Michell, Benito | Michell will review the document to select portions that require update. The editor will send the draft and Michell's analysis to Rod Chapman for action. | Closed | Done | 2012-03-28
Action | #19-02 | Benito | Contact the convener of WG9 and settle on a review schedule for the Ada and SPARK annexes. | Closed | Done | 2012-03-28
Action | #18-01 | Wagoner | Draft a C++ annex to use as a starter. Clive and John will support. | Closed | Larry has no plan to do this now; he has a new job. | 2011-12-14
Action | #17-06 | Benito | Send the baseline draft to WG14 for review, requesting comments in time for our meeting #23. | Closed | The C annex was well received when presented to WG14. | 2011-12-14
Action | #17-02 | Benito | Negotiate a review schedule with the Japanese Ruby group. Send them the baseline document with a request to revise the Ruby annex. | Closed | John has pinged the Ruby group with no results. John believes that they are OK with the annex. | 2011-12-14
Action | #19-03 | Benito | Incorporate N0366 into the baseline draft. | Closed |  | 2011-12-12
Action | #19-04 | Benito | Propose words in C.BJL to explain why the vulnerability is not applicable. | Closed |  | 2011-12-12
Action | #19-05 | Keaton | Propose a minor revision to 6.BJL to address the confusion in comment C.23 of N0361 | Closed | Included in N0376 | 2011-12-12
Action | #19-06 | Benito | Incorporate [N0369] into the baseline draft as a new Clause 8. | Closed |  | 2011-12-12
Action | #19-07 | Benito, Coyne, Pygott, Ploedereder | Coyne to revise Python annex. Pygott and Ploedereder to review. Benito to incorporate into baseline draft. | Closed |  | 2011-12-12
Action | #19-08 | Benito | Revise the NWIP for code signing, obtain appropriate review, and submit it for ballot along with the preliminary working draft. | Closed |  | 2011-12-12
Action | #17-20 | Wagoner, Johnson | Draft an annex for Python and send it and the baseline draft to the Python group for technical review. | Closed |  | 2011-12-12
Action | #19-01 | Benito | Determine the dates of Meeting #21 | Closed | See minutes of meeting #19. | 2011-10-05
Action | #18-03 | Benito, Ploedereder | Pick dates for Meeting #21. | Closed | See minutes of meeting #19. | 2011-10-05
Action | #18-04 | Benito, Michell | Reconfirm the Ottawa venue for Meeting #22 and select dates. | Closed | See minutes of meeting #19. | 2011-10-05
Action | #18-02 | Moore | Set up MeetingPlace for web conference for Meeting #19. | Closed | Benito set up ISO web conference facilties | 2011-10-01
Action | #18-06 | Moore | Draft additional text for 4.3 "How to Use this Document" that describes the language-specific annexes. | Closed | See N0365 | 2011-10-01
Action | #17-12 | Wagoner | Revise the code signing document according to comments in [N0318]. | Closed | See N0357 and N0359 | 2011-10-01
Action | #17-08 | Pygott | Invite persons interesting in software code signing to the Edinburgh meeting. | Closed |  | 2011-10-01
Action | #17-05 | Benito | Map the old MISRA-L comments [N0250] to the new baseline draft so that they may be considered at meeting #21. | Closed | See N0340 and N0342 | 2011-10-01
Action | #17-04 | Benito | Negotiate a review schedule for Ada and SPARK annexes with WG9. | Closed | Sent draft document | 2011-10-01
Action | #17-01 | All | Everyone is encouraged to submit a position paper by 15 May for a session on concurrency vulnerabilities at the Real-time Ada Workshop. (See AI #16-10). | Closed |  | 2011-10-01
Action | #16-10 | Michell | Explore the idea of a workshop for concurrency vulnerabilties at Real-time Ada Workshop is 14-16 September 2011 in Santander, Spain. | Closed | From Michell: I have submitted the concurrency Vulnerabilities to IRTAW 15 and I communicated with Alan Burns. I expect that there will be a session at IRTAW 15 on these. I will ask The program committee to invite WG 23 Members that could participate. | 2011-10-01
Action | #14-02 | Benito | Talk with Bjarne Stroustrup and Herb Sutter about possibilities for drafting a C++ annex by a graduate student or other parties outside WG21. | Closed | At a recent WG21 telecon, John received a good reaction to the idea of drafting an annex. | 2011-10-01
Action | #18-05 | Moore | Create a new document register for standing documents. | Closed | Done | 2011-06-27
Action | #17-21 | Benito | Add [N0331] to the baseline document. | Closed | Done | 2011-06-03
Action | #17-19 | Benito | Circulate the baseline-both PDF and DOC-for formal commenting by the beginning of May. Assign a particular section to every reviewer as well as requesting a general review. | Closed | Done | 2011-06-03
Action | #17-18 | Benito | Add [N0323] to the baseline. | Closed | Done | 2011-06-03
Action | #17-17 | Benito | Add [N0327] to the baseline. | Closed | Done | 2011-06-03
Action | #17-16 | Benito | Add [N0330] and any other changes to the Ada annex [N0296] and transmit it to WG9 for review, hopefully prior to the June meeting. | Closed | Done | 2011-06-03
Action | #17-15 | Benito | Add [N0329] to the baseline. | Closed | Done | 2011-06-03
Action | #17-14 | Benito | Add [N0326] to the baseline. | Closed | Done | 2011-06-03
Action | #17-13 | Benito | Add [N0322] to the baseline. | Closed | Done | 2011-06-03
Action | #17-11 | Benito | Add [N0332] to the baseline. | Closed | Done | 2011-06-03
Action | #17-10 | Benito | Add the C annex [N0304] to the baseline. | Closed | Done | 2011-06-03
Action | #17-09 | Benito | Create a baseline draft | Closed | Done | 2011-06-03
Action | #17-07 | Moore | Revise [N0321] and submit it for inclusion in the new baseline. | Closed | See N0332 | 2011-03-25
Action | #17-03 | Moore | Revise the schedule [N0302] to show PDTR ballot after the Dec 2011 meeting. | Closed | See N0333 | 2011-03-25
Action | #13-07 | Benito | Schedule an agenda item at a future meeting to consider the comments from MISRA L, N0250. | Closed | Replaced by #17-05 | 2011-03-25
Action | #16-08 | Karlin, Bob | Draft a vulnerability description for exception handling to deal with issues discussed in item 3.2 of document N0289. | Closed | See document N0319 | 2011-03-23
Action | #16-03 | Benito | Attempt to revitalize the liaison relationship with TC39 (ECMAScript) | Closed | John has been in touch. The contact does not seem to have interest. | 2011-03-23
Action | #16-02 | Benito | Designate a replacement for Tom Plum as liaison to Ecma International, TC49/TG2 (C#) | Closed | John has been in touch. The C# contact indicated interest in attending the Edinburgh meeting. | 2011-03-23
Action | #16-04 | Karlin, Beth | Prepare proposed revision of WXQ and YZS to deal with issues raised in item 3.1 of document N0289 and in document N0300. | Closed | See document N0316 | 2011-03-22
Action | #16-01 | Karlin, Bob | Follow-up with Cobol working group to identify someone to draft Cobol annex. | Closed | Bob may have found someone but it would not be possible to start until after May 2011. | 2011-03-22
Action | #16-13 | Ploedereder | Revise the Ada description of LAV based on comments noted in N0296. | Closed | See document N0311 | 2011-03-21
Action | #16-09 | Ploedereder | Propose more sensible words for section 1 of CLL. | Closed | Erhard responds: I could find nothing wrong with CLL both in the TR and the Ada Annex. (Maybe "CLL" was a typo in the minutes?) | 2011-03-21
Action | #16-07 | Ploedereder | Draft a vulnerability description for exception handling to deal with issues discussed in item 3.2 of document N0289. | Closed | See document N0312 | 2011-03-21
Action | #16-12 | Moore | Look at XYY in the main document and both annexes to try to tease apart two vulnerabilities: one concerning arithmetic over/underflow and one concerning performing bit/shift operations on numeric values. In both, note that unsigned and signed arithmetic present two different challenges. | Closed | See document N0305 | 2011-02-15
Action | #16-11 | Moore | Publish a document describing the schedule for production of the second edition of the TR. | Closed | See document N0302 | 2010-12-17
Action | #14-01 | Moore | Check if Meeting #20, December 2011, can be hosted at MITRE in McLean, VA | Closed | Meeting #20 scheduled for December 2011. | 2010-12-15
Action | #15-12 | Benito | Add CBF to the vulnerabilities as described in N0269. | Closed | Done- See N0286. | 2010-12-14
Action | #15-11 | Benito | Update the N0276 as described in section 3.7a of the minutes. | Closed | Done- See N0286. | 2010-12-14
Action | #15-10 | Benito | Update and reformat the language-specific annexes as described in section 3.3 of the minutes of Meeting #15. | Closed | Done- See N0286. | 2010-12-14
Action | #15-09 | Benito | Track ancestry of split or combined vulnerability descriptions as described in 3.12 of the minutes of Meeting #15. | Closed | Done- See N0286. | 2010-12-14
Action | #15-08 | Benito | Split XYR into two new descriptions as described in 3.10 of the minutes of Meeting #15. | Closed | Done- See N0286. | 2010-12-14
Action | #15-07 | Benito | Implement the combination of two vulnerabilities into the new HCB as described in 3.11 of the minutes of Meeting #15. | Closed | Done- See N0286. | 2010-12-14
Action | #15-06 | Benito | Move AJN to the clause on application vulnerabilities with the changes as described in section 4 of the minutes of Meeting #15. | Closed | Done- See N0286. | 2010-12-14
Action | #15-05 | Benito | Add to AJN the advice to eliminate control characters from file names. | Closed | Done- See N0286. | 2010-12-14
Action | #15-04 | Benito | Review the various descriptions in Clause 7, along with the new CBF, to determine if Implications for Standardization should be included, e.g. "provide library routines to assist in performing the checking." | Closed | Done- See N0286. | 2010-12-14
Action | #15-03 | Keaton | Propose a revision to XYQ that is more even-handed in describing legitimate reasons for dead code. | Closed | Done- See N0290 | 2010-12-14
Action | #13-03 | Vardanega | Try to colocate with a meeting of WG9 in June 2011 in Edinburgh. | Closed | Done | 2010-12-14
Action | #15-02 | Moore | Incorporate comments (see 3.6 of the minutes) into N0268 and provide the result [N0283] to the editor for use as the new baseline for the 2nd edition of 24772. | Closed | See N0283 | 2010-09-17
Action | #15-01 | Moore | Revise N0271 to describe the new preferred outline for language vulnerability descriptions as decided in Section 3.3 of the minutes of meeting #15. | Closed | See N0284 | 2010-09-17
Action | #14-06 | Karlin | Select a few of the Ada vulnerabilities and propose rewrites of them in newspaper style. He will track the time it requires to do this | Closed | OBE | 2010-09-17
Action | #14-12 | Michell | Discuss the prospect for a Fortran annex with the Canadian rep to WG5. | Closed | He seemed to be satisfied with the idea that Dan is handling it. There is little interest other than Dan's. | 2010-09-15
Action | #14-07 | Benito | Table [N0264], the request for free availability for consideration at the plenary meeting of SC 22. | Closed | The rationale is being forwarded to JTC 1 for action. | 2010-09-15
Action | #14-03 | Benito | Table [N0265], the NWIP for code signing, for consideration at the plenary meeting of SC 22. | Closed | Done. An SC22 letter ballot will be conducted. | 2010-09-15
Action | #13-05 | Benito | Circulate the draft C annex, N0245, to interested members of WG14 for comment. | Closed | Convener should circulate the revision that comes out of meeting #14 instead. | 2010-09-15
Action | #13-02 | Benito | Try to colocate a meeting of WG23 with WG14 in April 2011 or WG21 in March 2011. | Closed | The meeting is scheduled, colocated with WG 21. | 2010-09-15
Action | #09-01 | Benito and Nagle | Collaborate on a description of the logistics for handing annexes back and forth and dealing with comments with the goal that the language committee retains control over the technical content. | Closed | Obsolete | 2010-09-15
Action | #14-05 | Michell | Draft a table summarizing language vulnerabilities in a horizontal manner. | Closed | See N0280 for a prototype | 2010-09-14
Action | #14-11 | Chapman | Provide a SPARK annex | Closed | See N0275 | 2010-09-10
Action | #14-04 | Moore | Draft a table summarizing language vulnerabilities in a horizontal manner. | Closed | See N0279 for a prototype | 2010-09-10
Action | #14-09 | Pygott | Prepare a redline illustrating: Changing XYR into two descriptions that separate dead store from unused variable; Looking at the material in the Ada annex that defends unused variables and incorporating those reasons into the main body. | Closed | See N0272 | 2010-08-31
Action | #14-08 | Benito | Prepare a redline illustrating the following: Combining 6.19 and 6.22, called something like "Buffer Boundary Violation (Buffer Overflow)", dealing with both pointer and indexing violations; Focusing 6.20 on array indexing, if not already the case; and Focusing 6.21 of whole array operations, if not already the case. He will consider the language annexes as well as the body of the document. | Closed | See N0270 | 2010-08-31
Action | #14-10 | Moore | Prepare a redline of how the front matter should be slimmed down. This would include: Removing 4.2; Rewriting 4.3 to make it less wordy; Rewriting 4.4 to make it less wordy; Rewrite 5 in terms of predictability, moving most of it into an informative annex; In 6, move the general items (6.1 through 6.6) to the end and consider the possibility of a distinct clause for the general ones; If Annex A has any useful material, combine it with what's left of 5; Investigate separating the vulnerability outline so that Clause 6 and Clause 7 vulnerabilities are easily distinguished. | Closed | See N0268 | 2010-08-12
Action | #13-12 | Pygott and Sees | Investigate whether there are occurrences of vulnerabilities in hardware description languages, Clive should purse some contacts at York. | Closed | See N0263 | 2010-06-30
Action | #13-11 | Moore | Contact Sean Barnum to learn if he has any contacts who might be suitable for drafting an annex on a scripting language. | Closed | Sent note. Awaiting response. He suggested some names at Cigital. See 13-10. | 2010-06-27
Action | #13-10 | Wagoner | Contact Fortify (perhaps with the support of Paul Black) to participate in creating a draft annex for PHP. | Closed | Larry has identified someone to write a Python or PHP annex. | 2010-06-27
Action | #13-09 | Plum | Contact the liaison representative from EcmaScript to determine if he might be willing to draft an annex. | Closed | Plum wrote to Douglas Crockford. Was a helpful response received? See 13-10. | 2010-06-27
Action | #13-08 | Moore | Prior to meeting #14, draft a request for free availability as described in the minutes of meeting #13. | Closed | See N0262 | 2010-06-27
Action | #13-06 | Ploedereder | Ask WG9 to forward the darft Ada Annex and the draft SPARK annex to WG23 for consideration in planning the second edition of TR 24772, prior to June 25. | Closed | Received Ada; the SPARK annex was pushed back to Praxis for further work. This AI was closed and #14-11 was opened. | 2010-06-27
Action | #13-04 | Benito | Via email, call the working group members' attention to N0245 and request each individual to review the draft and send comments to Larry Wagoner by some given date. | Closed | Done | 2010-06-27
Action | #13-01 | Moore | Try to arrange a meeting of WG23 in San Diego, CA, USA for December 2010. | Closed | Meeting #16 is scheduled for 14-16 December 2010, in San Diego. | 2010-06-27
Action | #11-07 | Wagoner | Larry Wagoner volunteered to develop a version of the C annex where the mitigations are written in the form of rules rather than a discussion. | Closed |  | 2010-03-31
Action | #03-02 | Benito | Try to recruit Open Group (either UK and US) or others in the Java safety-critical. Contact Joe Bergmann. | Closed | Benito is corresponding with Andrew Josey. No decision yet. | 2010-03-30
Action | #12-02 | Plum | Check Hawaii for availability to host Meeting #14 during weeks of June 21 and June 28 | Closed |  | 2010-03-28
Action | #16-06 | Ploedereder | Draft a vulnerability description for circumventing language checking | Closed | See document N0313 | 2010-03-14
Action | #16-05 | Benito | Draft a vulnerability description for inter-language calling. | Closed | See document N0310 | 2010-03-14
Action | #11-05 | Moore | Send [N0203] to Ploedereder for revision and resubmission. | Closed | Done | 2009-10-21
Action | #09-03 | Michell | Re comment DMJ 5 of [N0159], propose a revision to more strongly differentiate between 6.19 and 6.20 of [N0138]. | Closed | Closed administratively | 2009-10-21
Action | #11-06 | Benito | Check the practicality of moving the November WG23 meeting to 21-23 October. | Closed | The meeting was rescheduled as suggested. | 2009-08-25
Action | #11-01 | Plum | Locate subject-matter experts on security in ECMAScript. | Closed | Tom replied in an email dated 25 July: "It appears that our liaison from Ecma TC39, Doug Crockford, is well qualified to comment on security questions. IIUC this completes my action item from ttawa, but I'm happy to assist in any way you would want, just let me know, ok?" | 2009-08-15
Action | #11-04 | Moore | Send the markup of the Ada-specific annex [N0205] to WG9. Also send the two new vulnerability descriptions from Michell: [N0213] and [N0214]. | Closed | Done | 2009-07-15
Action | #11-02 | Moore | Put the revised format for a language-specific annex in a document, post it, circulate it. | Closed | This was done immediately after the meeting as [N0217]. | 2009-07-15
Action | #09-02 | Michell | Revise and resubmit [N0155] to deal with issues raised during discussion at Meeting #9. | Closed | OBE | 2009-07-13
Action | #05-14 | Benito | Investigate CWE 365 (referenced in vulnerability description XYI) to determine what is intended. | Closed | Apparently the CWE description was revised. | 2009-06-22
Action | #10-07 | Benito | Complete the disposition of comments in [N0181] to create [N0187]. | Closed | Done | 2009-06-10
Action | #10-03 | Benito | Incorporate [N0182] in the next draft of 24772. | Closed | Done | 2009-06-10
Action | #10-02 | Benito | Complete the disposition of comments in [N0180] to create [N0184] | Closed | Done | 2009-06-10
Action | #10-01 | Benito and Moore | Update the schedule in N0167 as N0183. | Closed | Done | 2009-06-10
Action | #10-06 | Karlin | Look at the German comments on 6.26 that are contained in [N0181] and propose appropriate changes or rewrites. | Closed | See document N0190 | 2009-05-05
Action | #10-05 | Ploedereder, Wagoner | Perform an overall reconsideration of the content of Clause 5 and recommend actions to improve. Consider document [N0181], notably the general and technical comments by Belgium made on Clause 5 and its sub-clauses. | Closed | See document N0189 | 2009-05-04
Action | #10-04 | Moore | Create a list of issues that may be considered for a future revision. Include the following in the list: object-orientation, concurrency, scripting languages, and, possibly, additional material regarding floating-point arithmetic. Reference document [N0181], BE-05. | Closed | See document N0188 | 2009-04-19
Action | #09-12 | Pygott | Write a new vulnerability description on incomplete library specifications. | Closed | Document N0177 | 2009-04-13
Action | #09-11 | Ploedereder | Based, in part, on the draft of NSQ in [N0164], write a new description, SLH, for Clause 7 that involves verifying that you are actually calling the library that you intend to call. (Digital signing can be useful.) It will be considered for inclusion at the Dec 2008 editors' meeting. | Closed | Closed administratively | 2009-04-13
Action | #09-08 | Nagle | Make any desired changes to the draft in [N0164] of PUS for consideration at the Dec 2008 editors' meeting. | Closed | Nagle decided not to make changes. | 2009-04-13
Action | #09-07 | Moore | Update [N0130] in light of new meeting schedule and relog it. | Closed | Document N0167 | 2008-10-22
Action | #09-13 | Wagoner | Re comment CHP 36 of [N0159], propose a revision to 6.32. | Closed | Submitted to Benito for inclusion in next draft of TR | 2008-10-08
Action | #09-06 | Moore | Write a new description, DTK, based in part on the draft in [N0164]. Generalize it to deal with magic values and the ways that languages can deal with them. (Mention databases.) Put in 6 and note that the issues are often application issues but the solution is often language dependent. Mention that magic values should be outside the range permitted for the data values and mention that some languages lack the expressibility to ensure this. Moore took the action item to provide the revised description. It will be considered for inclusion at the Dec 2008 editors' meeting. | Closed |  | 2008-10-08
Action | #09-05 | Moore | Revise IHN as follows: add to the description of IHN that using a subtype that is too small, or a subtype with inadequate precision, might provide surprising results, particularly in array indexing, or numerical calculations where the number of calculations increase as a power of the problem size. | Closed |  | 2008-10-08
Action | #09-04 | Moore | Revise CSJ as follows: add to CSJ the problem if an out parameter (using call by result), is never assigned by the called subprogram. This acts like an uninitialized variable. It is difficult to see that the variable is not initialized. | Closed |  | 2008-10-08
Action | #09-09 | Nagle | Make any desired changes to the draft in [N0164] of NSQ for consideration at the Dec 2008 editors' meeting. Focus on the idea that prototypes are always needed. | Closed |  | 2008-10-05
Action | #08-27 | Benito | Ask Ishihata-san to ask Japanese NB to support changing OWGV to a WG | Closed | done | 2008-09-29
Action | #08-26 | Vardanega | Ask Italian NB to support changing OWGV to a WG | Closed | done | 2008-09-29
Action | #08-25 | Ploedereder | Ask Roman Grahle to ask German NB to support changing OWGV to a WG | Closed | done | 2008-09-29
Action | #08-24 | Plum | Ask US NB to support changing OWGV to a WG | Closed | done | 2008-09-29
Action | #08-23 | Michell | Ask Canadian NB to support changing OWGV to a WG | Closed | done | 2008-09-29
Action | #08-22 | Benito | Make improvments to PDTR as follows: 6.14.1 - the notes should be removed - Editor will do this 6.22.5 - Editor will delete first bullet and the note following the second bullet 6.26.1 - Editor will delete the note 6.31.7 - Delete first question. For second question, delete the sentence 6.40.6 - Editor will fix | Closed | Closed by the draft considered at meeting 9 | 2008-09-29
Action | #08-19 | Benito | Consider editorial corrections suggested by Wagoner in N0132. | Closed | Closed by the draft considered at meeting 9 | 2008-09-29
Action | #08-16 | Benito | Subject to the editor's discretion after a conversation with Seacord, add the cross-references from [N0124] to the draft PDTR noting any disagreements that arise. Send result to MISRA C, MISRA C++, CERT, and CWE for possible corrections. Clive volunteered to do the review for MISRA C++. | Closed | Closed by the draft considered at meeting 9 | 2008-09-29
Action | #08-14 | Plum | Create globally consistent terminology for length, size, count and bound. | Closed | done | 2008-09-29
Action | #08-13 | Pygott | Revise 6.15.5 and 6.15.6 (XZH, Off-by-one error) to sort out applicable language characteristics from means of avoidance. | Closed | done | 2008-09-29
Action | #08-12 | Plum | Revise XZB and XYW to reflect our agreement re CWE terminology | Closed | done | 2008-09-29
Action | #08-05 | Plum | Revise HFC, Pointer casting and pointer type changes | Closed | done | 2008-09-29
Action | #08-03 | Pygott | Provide definitions for safety terms in Clause 3 of PDTR, including "safety hazard" | Closed | Partially done in meeting #8. Administratively closed. | 2008-09-29
Action | #07-04 | Jones | Develop an example for clause 5.2 of the TR, "Issues arising from human cognitive limitations". | Closed | Included in Derek's comments | 2008-09-29
Action | #05-16 | Plum and Benito | Contact ECMA TC39/TG1 regarding security of ECMAScript. | Closed | done | 2008-09-29
Action | #09-10 | Nagle | Revise his proposal [N0145] to deal with comments from the Fortran editor [N0149] and the revised template for language-specific annexes [N0165] and submit it to WG5. Ultimately, it will be sent back to us for inclusion in the TR. | Closed | See N0198 | 2008-06-22
Action | #08-21 | Stoughton | For 7.10.6, write implications for standardization and make any other needed corrections. | Closed | Draft provided to editor | 2008-06-05
Action | #08-20 | Nagle | Answer questions about Fortran currently in 6.9.2 | Closed | Draft provided to editor | 2008-06-05
Action | #08-18 | Jones | It was decided that Derek might post N0121 to his web site and that the draft TR might reference the URL in its bibliography. | Closed |  | 2008-06-05
Action | #08-17 | Jones | It was noted that there are too many papers listed in N0122 to include in the TR. Derek was given an action item to recommend two or three for inclusion in the generic description of array bounds checking. Also, the document will be retained as a resource for usage in language dependent annexes. It was suggested that Derek might put this on his web site -- along with some appropriate annotations -- and that we might reference the web site in the bibliography of the TR. | Closed |  | 2008-06-05
Action | #08-15 | Moore | Update and reissue vulnerability description template with changes agreed at Meeting #8. | Closed | Draft provided to editor | 2008-06-05
Action | #08-10 | Pygott | Provide references for BVQ | Closed |  | 2008-06-05
Action | #08-09 | Wagoner | Provide new vulnerability description on "String termination" | Closed |  | 2008-06-05
Action | #08-08 | Wagoner | Revise NYY, Dynamically linked code and self-modifying code | Closed | Draft provided to editor | 2008-06-05
Action | #08-07 | Moore | Revise CLL, Switch statements and static analysis | Closed | Draft provided to editor | 2008-06-05
Action | #08-06 | Moore | Revise BRS, Leveraging human experience | Closed | Draft provided to editor | 2008-06-05
Action | #08-04 | Wagoner | Revise EOJ, Demarcation of Control Flow | Closed | For mechanism of failure in EOJ, the text should be: "The failure occurs because the language compiler determines the control flow to be different than the control flow intended by the programmer. Therefore the program executes differently than intended." | 2008-06-05
Action | #08-02 | Moore | Write Section 1.5, How to Use this Document, for the PDTR | Closed | Draft provided to editor | 2008-06-05
Action | #08-11 | Plum | Rewrite PLF separating representation issues from numeric issues | Closed | See minutes of meeting #8 | 2008-04-11
Action | #08-01 | Stoughton | Write an introduction for the PDTR | Closed | See minutes of meeting #8 | 2008-04-11
Action | #07-05 | Moore | Compose a spreadsheet for providing comments on vulnerability descriptions. | Closed | Completed. | 2008-04-09
Action | #07-03 | Moore | Seek a liaison relationship between SC22 and SC27 on the development of coding guidelines to support security. Suggest that an appropriate interface between their work and our work is for them to suggest capabilities that should be included in programming languages, language libraries, and APIs for use by those performing application security. Investigate co-locating with INCITS CS1 at a west-coast local for Meeting #11 (or possibly Meeting #9). Investigate colocating SC27/WG4. | Closed | Consolidates #03-03, #04-07, and #05-15. Doesn't seem possible at this time. | 2008-04-09
Action | #07-02 | Pygott | Determine if the OWGV can get access to a draft of DO-178C. | Closed | Anyone who wants access can sign up for the working group. | 2008-04-09
Action | #06-01 | Plum | Consider the practicality of a set of vulnerability descriptions related to object-oriented programming. Consider JSF C++ rules 70 thru 100, 177, 178, 179, 185, 219, as well as OOTIA. | Closed | Tom has solicited comments with little result. | 2008-04-09
Action | #05-13 | Plum | Provide wording for "RSIZE_T" and "Verifiably representable" for vulnerability description XYE. | Closed | The wording ended up in FLC. | 2008-04-09
Action | #05-11 | Jones | Resubmit vulnerability descriptions with changes as suggested in Meeting #5. | Closed | Incorporated into draft TR | 2008-04-09
Action | #05-03 | Jones | Revise N0078 to describe how "processor-dependent" or "implementation-dependent" features of various programming languages can be located in their respective standards. | Closed | Document was updated. | 2008-04-09
Action | #05-01 | Jones | Revise N0078 in accordance with Decision Log Item #05-01, and in Table .1, change the "No" for Java to "yes". | Closed | Document was updated. | 2008-04-09
Action | #05-12 | Michell | Review safety documents (e.g. 61508, DO178B) to look for safety hazards that might be treated in the TR. | Closed | Document N0116 | 2007-12-16
Action | #07-01 | Seacord | Propose a set of categories useful in making distinctions of code written by hand and code generated by tools. | Closed | Closed with document N0114 | 2007-12-15
Action | #04-01 | Jones | Provide his list of available coding standards for C, C++, Java, and Ada to John Benito for addition to the Bibliography of the TR. | Closed | Document N0113 | 2007-12-14
Action | #05-15 | Moore | Contact SC27/WG4 and suggest that an appropriate interface between their work and our work is for them to suggest capabilities that should be included in programming languages, language libraries, and APIs for use by those performing application security. | Closed | Consolidated into #07-03. | 2007-12-12
Action | #05-07 | All | Recommend additional items for the Bibliography of the TR | Closed |  | 2007-12-12
Action | #05-06 | Plum | Ask CWE to change the names of "Stack Overflow" and "Heap Overflow" to "Buffer Overflow in Stack" and "Buffer Overflow in Heap". Also ask them to change "Process Control" to "Executing or Loading Untrusted Code". | Closed | CWE responded that this is part of a larger terminology rewrite. | 2007-12-12
Action | #04-07 | Moore | Investigate co-locating with INCITS CS1 at a west-coast local for Meeting #11 (or possibly Meeting #9). Investigate colocating SC27/WG4. | Closed | Consolidated into #07-03. | 2007-12-12
Action | #03-03 | Moore | Seek a liaison relationship between SC22 and SC27 on the development of coding guidelines to support security. | Closed | Consolidated into #07-03. | 2007-12-12
Action | #01-08 | Benito | Obtain a liaison representative from WG21. | Closed | WG21 has established liaison with OWGV. | 2007-10-25
Action | #05-08 | Benito | Add TR 24731 to the Bibliography of the draft TR. | Closed |  | 2007-10-01
Action | #03-01 | Moore | Invite a representative from the Lockheed-Martin JSF team that developed the C++ guidelines. | Closed | Unsuccessful, but Wagoner considered the JSF guidelines in his proposal. | 2007-10-01
Action | #05-10 | Wagoner | Resubmit vulnerability descriptions with changes as suggested in Meeting #5. | Closed | Done | 2007-09-04
Action | #05-09 | Benito | Submit the draft of the TR to SC22 by the time of the deadline permitting it to be considered for registration at the plenary meeting. | Closed | Done | 2007-09-04
Action | #05-05 | Benito | Incorporate N0090 in the next version of the TR. | Closed | Incorporated in draft 070806 | 2007-09-04
Action | #05-04 | Benito | For meeting #6, table the question of whether there should be a rationale document. | Closed | Added to preliminary agenda, N0097 | 2007-09-04
Action | #05-02 | Benito | Incorporate N0091 in the next version of the TR. | Closed | Incorporated in draft 070806 | 2007-09-04
Action | #04-02 | Moore and Benito | Cull the decision log to retire implemented decisions from the log. | Closed |  | 2007-07-18
Action | #02-09 | Hills | Write articles for "IT Security" and "UK Embedded Systems Engineering" regarding the work of the OWGV. | Closed | Administratively closed | 2007-07-18
Action | #02-08 | Hills | Propose a list of vulnerabilities and appropriate facets for classification. | Closed | Administratively closed | 2007-07-18
Action | #02-03 | Michell | Make a contribution describing how to apply TR 15942 in the work of the OWGV. | Closed |  | 2007-07-18
Action | #04-25 | ALL | The current list of issues contained in subclause 5.5 of N0061 can become candidates for inclusion in Clause 8. Persons who proposed them should be proposed again in the form of the new template, N0072. | Closed |  | 2007-07-16
Action | #04-24 | Michell | Re-propose the draft content of clause 7 of [N0061] as a list of proposed vulnerabilities, using the new template [N0072]. | Closed | OBE | 2007-07-16
Action | #04-22 | Moore | Submit draft material to Benito for the sub-section of 1.4 dealing with the audience interested in assurance. | Closed |  | 2007-07-16
Action | #04-21 | Wagoner | Submit draft material to Benito for the sub-section of 1.4 dealing with the audience interested in security. | Closed |  | 2007-07-16
Action | #04-20 | Jones | Submit draft material to Benito for the sub-section of 1.4 dealing with the audience interested in safety. | Closed |  | 2007-07-16
Action | #04-19 | Nagle | Submit draft material to Benito for the sub-section of 1.4 dealing with the audience interested in predictability. | Closed |  | 2007-07-16
Action | #04-17 | Wagoner | Revise his analysis in accordance with the discussion described in item 3.9 of Meeting #4 and resubmit as document N0073. The vulnerabilities should be described as instances of the new template N0072. | Closed |  | 2007-07-16
Action | #04-11 | Jones | Revise N0060 in light of discussion at Meeting #4 and resubmit to OWGV. | Closed |  | 2007-07-16
Action | #04-09 | Moore and Benito | Do pre-meeting mailing for Meeting #5 circa 29 June 2008. | Closed |  | 2007-07-16
Action | #04-03 | Benito | Select precise dates for Meeting #7 in Pittsburgh, PA | Closed |  | 2007-07-16
Action | #04-27 | Benito | Implement the changes to the TR described in item 3.8 of Meeting #4 to create N0074. | Closed |  | 2007-06-30
Action | #04-23 | Benito and Plum | Try to integrate some of the other definitions from Tom Plum's paper, N0062, into the definitions of the draft TR. | Closed |  | 2007-06-30
Action | #04-16 | Benito | Add a citation of Seacord's document [N0059] to the Bibliography of the TR. | Closed |  | 2007-06-30
Action | #04-15 | Moore | Revise Version 4 of the template for vulnerability descriptions in N0056 to produce a new template N0072. Revisions include (1) in the content of the example, mention matching integer ranges to array sizes; (2) use explicit tags for all fields, not just the first few; (3) provide both an empty template and a worked example of array indexing; (4) add cross-reference to CWE leaf node identifiers; (5) the identifier should be a unique, immutable ID; (6) add a categorization giving a backward link to the relevant sub-section of Clause 5 and any other relevant classification facets. | Closed |  | 2007-06-30
Action | #04-14 | Benito | Contact vendors for Eiffel, PHP and Perl regarding participation in OWGV. | Closed |  | 2007-06-30
Action | #04-13 | Benito | Add RTCA DO-178B to the bibliography of the draft TR. | Closed |  | 2007-06-30
Action | #04-12 | Benito | Update the draft TR to use the definition of "language vulnerability" from Tom's paper as amended during discussion by the addition of the words "or combination of features". | Closed | Completed | 2007-06-30
Action | #04-10 | Moore and Seacord | They are requested to mention favorable feedback from J3 and WG14 in their upcoming presentation at the SSTC conference. | Closed | Done | 2007-06-30
Action | #04-08 | Moore and Benito | Do post-meeting mailing for Meeting #4 circa 1 June 2008. | Closed | Completed on 4 June. | 2007-06-30
Action | #04-06 | Benito | Ask Erhard Ploedereder if he could host a Meeting #10 in Stuttgart in September or early October 2008. | Closed | Completed. Meeting is tentatively planned for Stuttgart. | 2007-06-30
Action | #04-04 | Benito | Discuss with William Wakker the possibility of holding Meeting #8 in Delft or Amsterdam during April 7-11, 2008. | Closed | Completed. Meeting is tentatively planned for Amsterdam | 2007-06-30
Action | #01-11 | Benito and Jaeschke | Obtain a liaison representative from Eiffel. | Closed | Tom and John have made contact with no result so far. | 2007-06-30
Action | #04-28 | Moore | Send a response to SC27 in behalf of OWGV (cc-ing SC 22 leadership) that a part of their proposals overlaps the work of OWGV. Mention that we are preparing an invitation for co-located meetings of WG4 and OWGV. | Closed | Done | 2007-06-01
Action | #04-26 | Nagle | Rewrite the current clause 5, subclauses 5.1 through 5.4, of N0061 with the goal of making it generic and consistent. | Closed | Submitted to Benito for inclusion in next draft of TR | 2007-06-01
Action | #04-05 | Benito | Check if INCITS is available for Meeting #9 during July 14-18, 2008. | Closed | A room at INCITS has been reserved. | 2007-06-01
Action | #04-18 | Moore | Add a link to the Wiki to the OWGV web site. | Closed | The link was added at the bottom of the Document Log page. | 2007-05-02
Action | #03-05 | Michell | Rewrite section 1.3 of N0040 to improve its readability. | Closed | Administratively closed | 2007-05-02
Action | #03-04 | Jones | For some of the languages of interest, provide a cross-reference for the terms that the languages use for "implementation-defined," "unspecified", etc. | Closed | Included in document N0060. | 2007-04-05
Action | #02-12 | Caseley | Send the convener a cleared version of the presentation made at Meeting #2. | Closed | Posted as document N0041 | 2007-04-05
Action | #02-06 | Ploedereder | Propose a list of vulnerabilities and appropriate facets for classification. | Closed | Closed administratively | 2007-04-05
Action | #02-11 | Caseley | Ask if any NATO countries are interested in hosting a meeting of OWGV. | Closed | Closed administratively | 2006-12-12
Action | #02-10 | Benito | Confer with the Netherlands national body regarding hosting a meeting of OWGV. | Closed | Netherland is willing to host a meeting. | 2006-12-12
Action | #01-13 | Benito and Moore | Follow up on current discussions with Java representative. | Closed | The convener has followed up but with no success. Replaced with AI 03-02. | 2006-12-12
Action | #01-06 | Spees | Consider making arrangements to be accredited as a US delegate. Contact Rex Jaeschke. | Closed | Closed administratively | 2006-12-12
Action | #02-05 | Michell | Propose a list of vulnerabilities taken from ISO/IEC 15942 and appropriate facets for classification. | Closed | Provided as document N0048. | 2006-11-10
Action | #02-04 | Benito and Moore | Synthesize a document outline from Moore's proposal, as amended by the meeting, and the UK base document, as amended by the meeting. Prepare the outline in time for distribution via the post-meeting package. | Closed | John Benito prepared document N0040. | 2006-11-10
Action | #01-09 | Plum and Seacord | Produce a proposal for "levels" to be used. | Closed | Discussion is underway between Tom Plum and Robert Seacord. Plum suggested that some other concepts need to be agreed upon, such as 'critical vulnerability', before a scheme of 'levels' could be developed. Seacord submitted a chart showing the CERT approach. | 2006-11-10
Action | #02-01 | Benito | Contact SC22 representatives who voted for the work item and ask them if they will host a meeting of OWGV. | Closed | Germany, Japan and Netherlands are considering hosting. | 2006-09-24
Action | #02-07 | Pygott | Propose classification facets based on the QinetiQ work. | Closed | Provided as document N0044. | 2006-09-19
Action | #02-02 | Pygott | Make the QinetiQ report on vulnerabilities available to OWGV. | Closed | Provided as document N0043. | 2006-09-19
Action | #01-05 | Pygott | Request MISRA C++ to designate him, or someone else, as their liaison representative to OWGV. | Closed | Clive has been appointed as liaison from MISRA C++. He forwarded the email note making the appointment. | 2006-09-19
Action | #01-16 | Benito | Arrange for colocating meeting with C Working Group in UK during April 2007. | Closed | Dates are unclear | 2006-09-14
Action | #01-10 | Moore, Wagoner, and Jones | Produce a more complete proposal for Moore's "half-baked" idea for organizing the report. | Closed | Moore has prepared a proposal. Wagoner and Jones do not agree. The proposal will be discussed at meeting #2. | 2006-09-12
Action | #01-14 | Plum | Request C# to designate him, or someone else, as their liaison representative to OWGV. | Closed | Completed. Tom Plum has been designated liaison from ECMA TC39/TG2. | 2006-08-11
Action | #01-15 | Benito | Arrange for meeting in Washington, DC during week of 11-15 Dec 2006. | Closed | Meeting #3 is scheduled for Washington, DC, 11-13 December 2006. | 2006-07-31
Action | #01-12 | Moore | Confirm that someone will represent Cobol. | Closed | Barry Tauber was appointed as liaison from J4 and WG4. | 2006-07-31
Action | #01-07 | Nagle | Request WG5 (Fortran) to designate him, or someone else, as their liaison representative to OWGV. | Closed | Dan Nagle was appointed as liaison from J3 and WG5. | 2006-07-31
Action | #01-01 | Jones | Investigate the possibility of scheduling a third day for Meeting #2 in London. | Closed | Not possible. However, there could be a meeting of a subgroup on the following Monday. | 2006-07-31
Action | #01-04 | Moore | Create a new email reflector named, roughly, SC22 OWGV. Ask people on the current mailer if they wish to be on the new one. Check into the possibility of options to place a prefix in the subject line and sequentially number the messages. | Closed | Completed. A subject prefix has been implemented but sequential numbering does not appear to be supported by the mailer software that is available to me. | 2006-06-30
Action | #01-03 | Moore | On the web site, change the "Resources" page to "Links". | Closed | Completed. | 2006-06-30
Action | #01-02 | Moore | Update the proposed FAQ and place the resulting material on the web site. | Closed | Completed. | 2006-06-30

## Decision Log
Decision Log for ISO/IEC JTC 1/SC 22/OWGV |  |  | Updated: | 2009-04-16 08:49
Label | Mtg-Item Number | Item | Type | Status | Comments | Date of Last Status
Decision | #02-09 | Use a faceted classification scheme as a method of organizing the vulnerabilities. | Document | Tentative |  | 2007-07-16
Decision | #02-12 | Consequence and cost of remediation are important in discussion of "levels". In the technical report, we would treat these issues but not in a numerical fashion. Instead, we would treat them in a narrative fashion. With respect to the possible factor of likelihood, exploitable vulnerabilities should be regarded as having a likelihood of 100%. | Document | Tentative
Decision | #02-15 | Guidelines considered but rejected should be described in a Rationale section. | Document | Tentative |  | 2007-07-16
Decision | #02-16 | A rule about meaningful variable names is not currently practical because it is culture-dependent and the data and algorithms needed to enforce such a rule are not available. It is an example of an item that should be put into the rationale as a rejected rule. | Content | Tentative | Wording revised during review of minutes of Meeting #2, 28 Sep 2006
Decision | #02-17 | Binary operator precedence can be a problem because there is empirical evidence of large percentage of mistakes. Alternatives include inserting parentheses in problematic cases, use of temporary variables for subexpressions, (inlined) function calls, and the use of analyzers that call out cases with unusual operators and a lot of parentheses. Rules can be checked automatically. Computing a complex Boolean in a temporary variable is a solution superior to creating a complex branching structure. | Content | Tentative | Wording revised during review of minutes of Meeting #2, 28 Sep 2006
Decision | #03-03 | Distinguish the notions of formally predictable behaviour and pragmatically expected behaviour and state that the approach taken by the TR is closer to the latter. | Document | Tentative |  | 2007-07-16
Decision | #03-09 | The approach to a guideline for floating point should be "get help from a numerical analyst. We would like the approach to concurrency to be similar but have not settled on a treatment. | Document | Tentative |  | 2007-07-16
Decision | #03-11 | Rationale for the Technical Report should be in a distinct document that is freely available on a web site. Wiki technology might be an interesting way to draft the document. | Document | Tentative |  | 2007-07-16
Decision | #04-02 | When we describe a vulnerability that appears in CWE as a leaf node, then we should cross-reference our description to the CWE leaf node identifier. | Document | Tentative
Decision | #05-01 | A successor to N0078 might be used in a rationale for the TR or referenced in the bibliography of the TR. The document should be revised to be more of a manual, answering questions for each language like the following: where is the language specified; where is the library specified; how does the standard describe implementation-defined behavior; etc. | Document | Tentative |  | 2007-07-20
Decision | #05-02 | As specific examples of the catch-all vulnerabilities are discovered, they should be added to the set as distinct vulnerabilities. | Content | Tentative |  | 2007-07-20
Decision | #01-01 | Although we will normally rely on liaisons to report back to their organizations as they see fit, the OWGV will occasionally create official documents for transmission to organizations in liaison. | Procedural | Continuing
Decision | #01-02 | In general, we will schedule future meetings for 3 or 3-1/2 days. | Procedural | Continuing |  | 2007-07-16
Decision | #01-04 | It was decided that prior to each meeting, the officers should gather the relevant documents into a pre-meeting package for distribution. Similarly, after each meeting, a post-meeting package should be distributed. Documents should be harvested from each meeting's Wiki for posting in the document log of the web site and for inclusion in the post-meeting package. | Procedural | Continuing
Decision | #01-05 | The OWGV should remain open to participation, but stop short of permitting individual free-lancers. We would want organizations in liaison to affirmatively designate their representatives, but we don't have to go so far as to require formal Category C liaison. | Procedural | Continuing
Decision | #02-01 | The OWGV Technical Report should be organized around generic descriptions of weaknesses. Annexes will provide the language-dependent descriptions of the weaknesses. Our liaison representatives would ensure that the language committees provide appropriate material to be used in the annexes. | Document | Continuing |  | 2007-07-16
Decision | #02-03 | We prefer guidance based on evidence. It should be acceptable to provide rules based on preponderence of expert belief, but the rationale should explain the basis for belief so that readers can determine if the rule is applicable to their situation. | Document | Continuing |  | 2007-07-16
Decision | #02-04 | OWGV will recommend to SC 22 that OWGV should be continued for another year with John Benito as convener and Jim Moore as secretariat. | Procedural | Continuing | Will forward to SC22 plenary.
Decision | #02-05 | OWGV will view "predictability" not as a mathematically provable property but as an ideal that we hope to approach. We would apply the test that a piece of code is not "predictable" if it is possible for it to violate the model of execution understood by a "reasonably competent programmer". | Document | Continuing |  | 2007-07-16
Decision | #03-01 | For future meetings, we decided to add an agenda item to review the decision log of the previous meeting. | Procedural | Continuing |  | 2007-07-16
Decision | #04-05 | All proposals for vulnerabilities should be submitted in the form of Version 5 of the template N0072. | Procedural | Continuing |  | 2007-07-16
Decision | #01-03 | Request SC22 to remove "[language selection]" from the title of the project. | Work programme | Closed | OBE | 2007-07-16
Decision | #02-02 | We will ask the language committees for a list of all "processor-dependent" or "implementation-dependent" features of their languages. | Document | Closed | Replaced with Action Item #05-03. | 2007-07-20
Decision | #02-06 | Step-wise predictability is a useful criterion for providing advice, at least when considering serial execution. (Note that some non-determinism is permitted.) | Document | Closed | Replaced by #03-03 | 2007-07-16
Decision | #02-07 | View floating point and concurrent execution as "out of bounds" at least for starters. | Document | Closed | Replaced by #03-09 | 2007-07-16
Decision | #02-08 | Use Wichmann's section 3 of [N0032] as a starting point for a categorization of problem areas in language description (but not language usage). | Document | Closed | OBE | 2007-07-16
Decision | #02-10 | The reference in [N0030] to "dialects" risks leading us into vendor-specific issues. Remove the reference to dialects. | Document | Closed | OBE | 2007-07-16
Decision | #02-11 | Remove the section on profiles from [N0030]. Instead, give advice on writing profiles. Profiles might arise from the faceted classification scheme. | Document | Closed | OBE | 2007-07-16
Decision | #02-13 | In developing a draft Technical Report, implement the decisions of Meeting #2 with respect to the UK proposal for a base document. | Document | Closed | OBE | 2007-07-16
Decision | #02-14 | Describing vulnerabilities (as described in the New Work Item Proposal) is distinct from guidance on how to produce language-specific guidelines (as suggested by the UK proposal). The latter can be regarded as a future work item. If material appropriate to this is produced, we will save it for potential future work items. | Work programme | Closed | Replaced by #03-10 | 2007-07-16
Decision | #03-02 | Use definitions of (language) vulnerability, (application vulnerabilty), (security) vulnerability, (safety) hazard, and predictable execution drafted in item 3.6 of meeting #3. | Document | Closed | Implemented in draft TR. | 2007-07-16
Decision | #03-04 | Some of the guidelines proposed by Derek Jones in N0051 might be reworded as the top-level organization of the clause of the TR that describes the vulnerabilities in language-independent form. See section 3.6 of N0055. | Document | Closed | Implemented in draft TR. | 2007-07-16
Decision | #03-05 | Future working drafts of the Technical Report should include line numbering for easy reference. | Procedural | Closed | Implemented in draft TR. | 2007-07-16
Decision | #03-06 | Move the current references into a bibliography annex and add the language standards to the bibliography. | Document | Closed | Implemented in draft TR. | 2007-07-16
Decision | #03-07 | Add a section 1.4 to discuss intended audience. | Document | Closed | Implemented in draft TR. | 2007-07-16
Decision | #03-08 | Incorporate the various decisions made for issues in Clause 5 of the draft TR. Reference section 3.6 of N0055. | Document | Closed | Implemented in draft TR. | 2007-07-16
Decision | #03-10 | We should include guidance on writing profiles that take advantage of the guidance in the Technical Report. | Document | Closed | Implemented in draft TR. | 2007-07-16
Decision | #04-01 | Drafts of the evolving Technical Report should be made available whenever ready rather than waiting for the next pre-meeting or post-meeting mailing. | Procedural | Closed | Implemented in draft TR. | 2007-07-16
Decision | #04-03 | Convert the draft TR to Wiki format; Persons who are given action items to make changes will be given edit privileges; They should annotate their changes with the action item number for traceability. | Document | Closed | Found to be impractical | 2007-07-16
Decision | #04-04 | Clause 1.4 should describe 4 primary audiences -- safety, security, predictability (non-software-engineering-types-getting it right the first time), and assurance. | Document | Closed | Implemented in draft TR. | 2007-07-16